## Schedule
Day | Date | Order | Start | Item | Scene | I/E | D/N | Heading | Location | Synopsis | Cast | Pages | Est. time | Notes
Shoot Day 1 | Mon 11 Jan 2027 | 1 | 08:00 | Scene | 28 | INT | Day | INT. COAST RADIO STATION - TAPE ROOM - DAY | Coast Radio Station (Old Signal Station, Vypin) | In the flooded basement they find the station logbook in a sealed ammunition box. | SURESH (Sajan Kuriakose), RAHUL (Aditya Nair), ANJALI (Nimisha Raghavan) | 1 2/8 | 4h
Shoot Day 1 | Mon 11 Jan 2027 | 2 | 12:00 | Scene | 29 | INT | Day | INT. COAST RADIO STATION - OPERATIONS ROOM - DAY | Coast Radio Station (Old Signal Station, Vypin) | The logbook: entries stop at 23:40. 'Main power cut by order. J. D'Cruz.' | SURESH (Sajan Kuriakose), RAHUL (Aditya Nair), JOE (Lal Fernandez), ANJALI (Nimisha Raghavan) | 1 4/8 | 2h 30m
Shoot Day 1 | Mon 11 Jan 2027 | 3 | 13:00 | Lunch |  |  |  | LUNCH at 13:00 (1h)
Shoot Day 2 | Tue 12 Jan 2027 | 1 | 15:00 | Scene | 2 | INT | Night | INT. COAST RADIO STATION - OPERATIONS ROOM - NIGHT (1999) | Coast Radio Station (Old Signal Station, Vypin) | Mariamma at the transmitter. Young Anjali asleep under the desk. The lights die. | MARIAMMA (Divya Mathew), YOUNG ANJALI (Ameya Suresh), JOE (Lal Fernandez) | 1 2/8 | 4h
Shoot Day 2 | Tue 12 Jan 2027 | 2 | 19:00 | Scene | 33 | INT | Night | INT. COAST RADIO STATION - OPERATIONS ROOM - NIGHT (1999) | Coast Radio Station (Old Signal Station, Vypin) | Flashback. In the dark Mariamma connects the battery set. Joe leaves. Young Anjali watche… | JOE (Lal Fernandez), MARIAMMA (Divya Mathew), YOUNG ANJALI (Ameya Suresh) | 1 6/8 | 4h
Shoot Day 2 | Tue 12 Jan 2027 | 3 | 23:00 | Scene | 11 | INT | Night | INT. COAST RADIO STATION - OPERATIONS ROOM - NIGHT | Coast Radio Station (Old Signal Station, Vypin) | Anjali and Rahul let themselves in. The tape shelves are empty except for one reel dated … | RAHUL (Aditya Nair), ANJALI (Nimisha Raghavan) | 1 3/8 | 3h
Shoot Day 2 | Tue 12 Jan 2027 | 4 | 19:30 | Dinner |  |  |  | DINNER at 19:30 (45m)
Shoot Day 3 | Wed 13 Jan 2027 | 1 | 18:00 | Scene | 12 | EXT | Night | EXT. COAST RADIO STATION - NIGHT | Coast Radio Station (Old Signal Station, Vypin) | A security guard spots their torches. They run. Rahul's bicycle chain comes off. | Guard, RAHUL (Aditya Nair), ANJALI (Nimisha Raghavan) | 1 1/8 | 3h
Shoot Day 3 | Wed 13 Jan 2027 | 2 | 21:00 | Scene | 41 | EXT | Night | EXT. COAST RADIO STATION - ROOF - NIGHT | Coast Radio Station (Old Signal Station, Vypin) | Rahul and Anjali send the broadcast out from the old mast one last time. | RAHUL (Aditya Nair), MARIAMMA (Divya Mathew), ANJALI (Nimisha Raghavan) | 1 3/8 | 3h
Shoot Day 3 | Wed 13 Jan 2027 | 3 | 05:50 (+1) | Scene | 5 | EXT | Day | EXT. COAST RADIO STATION - DAWN | Coast Radio Station (Old Signal Station, Vypin) | Anjali arrives. Appachan sits at the foot of the mast with his dog Kannan. Inspector Lath… | LATHA (Reshmi Pillai), APPACHAN (K. P. Gopinathan), ANJALI (Nimisha Raghavan) | 1 3/8 | 3h 30m
Shoot Day 3 | Wed 13 Jan 2027 | 4 | 23:00 | Night lunch |  |  |  | NIGHT LUNCH at 23:00 (45m)
Shoot Day 4 | Thu 14 Jan 2027 | 1 | 08:00 | Scene | 6 | INT | Day | INT. THOMAS HOUSE - KITCHEN - DAY | Thomas House (private home, Chellanam) | Tea with Fathima. The Port Trust notice on the fridge: demolition in seven days. | FATHIMA (Sabitha Rasheed), APPACHAN (K. P. Gopinathan), ANJALI (Nimisha Raghavan) | 1 3/8 | 2h 30m
Shoot Day 4 | Thu 14 Jan 2027 | 2 | 10:30 | Scene | 15 | INT | Day | INT. THOMAS HOUSE - VERANDA - DAY | Thomas House (private home, Chellanam) | Appachan mistakes Anjali for Mariamma and scolds her for being late for her shift. | APPACHAN (K. P. Gopinathan), ANJALI (Nimisha Raghavan) | 1 | 1h 45m
Shoot Day 4 | Thu 14 Jan 2027 | 3 | 12:15 | Scene | 10 | INT | Night | INT. THOMAS HOUSE - APPACHAN'S ROOM - NIGHT | Thomas House (private home, Chellanam) | In a clear moment Appachan gives Anjali the station keys. He speaks in Malayalam. | APPACHAN (K. P. Gopinathan), MARIAMMA (Divya Mathew), ANJALI (Nimisha Raghavan) | 1 3/8 | 2h 30m
Shoot Day 4 | Thu 14 Jan 2027 | 4 | 14:45 | Scene | 39 | INT | Night | INT. THOMAS HOUSE - APPACHAN'S ROOM - DUSK | Thomas House (private home, Chellanam) | Appachan dresses in his best shirt and asks where Mariamma is. Anjali tells him gently. | APPACHAN (K. P. Gopinathan), ANJALI (Nimisha Raghavan) | 7/8 | 1h 30m
Shoot Day 4 | Thu 14 Jan 2027 | 5 | 16:15 | Scene | 20 | INT | Night | INT. THOMAS HOUSE - KITCHEN - NIGHT | Thomas House (private home, Chellanam) | Anjali and Fathima read the file. Fathima talks about her uncle for the first time. | FATHIMA (Sabitha Rasheed), ANJALI (Nimisha Raghavan) | 1 3/8 | 2h
Shoot Day 4 | Thu 14 Jan 2027 | 6 | 13:00 | Lunch |  |  |  | LUNCH at 13:00 (1h)
Shoot Day 5 | Fri 15 Jan 2027 | 1 | 09:00 | Scene | 9 | INT | Night | INT. FATHIMA'S TEA SHOP - NIGHT | Tea Shop and Toddy Shop Row (Mattancherry) | The school radio club meets over tea. Rahul asks Anjali to look at their homemade transmi… | MEENU (Gauri Krishna), RAHUL (Aditya Nair), FATHIMA (Sabitha Rasheed), Nurse, ANJALI (Nimisha Raghavan) | 2 | 3h 30m
Shoot Day 5 | Fri 15 Jan 2027 | 2 | 12:30 | Scene | 14 | INT | Day | INT. FATHIMA'S TEA SHOP - KITCHEN - DAY | Tea Shop and Toddy Shop Row (Mattancherry) | They bake the reel in a borrowed bakery convection oven, watched like a newborn. | RAHUL (Aditya Nair), FATHIMA (Sabitha Rasheed), MEENU (Gauri Krishna), ANJALI (Nimisha Raghavan) | 1 3/8 | 2h 15m
Shoot Day 5 | Fri 15 Jan 2027 | 3 | 14:45 | Scene | 17 | INT | Day | INT. JOE'S ROOM ABOVE THE TODDY SHOP - DAY | Tea Shop and Toddy Shop Row (Mattancherry) | Anjali visits Joe. He will not talk about that night and asks her to leave. | JOE (Lal Fernandez), ANJALI (Nimisha Raghavan) | 1 2/8 | 2h
Shoot Day 5 | Fri 15 Jan 2027 | 4 | 16:45 | Scene | 30 | EXT | Night | EXT. TODDY SHOP - NIGHT | Tea Shop and Toddy Shop Row (Mattancherry) | Anjali confronts Joe in front of the drinkers. He walks out to his car. | JOE (Lal Fernandez), SURESH (Sajan Kuriakose), ANJALI (Nimisha Raghavan) | 1 1/8 | 3h
Shoot Day 5 | Fri 15 Jan 2027 | 5 | 13:30 | Lunch |  |  |  | LUNCH at 13:30 (1h)
Shoot Day 5 | Fri 15 Jan 2027 | 6 | 18:00 | Tea shop to toddy shop yard (same street) |  |  |  | TEA SHOP TO TODDY SHOP YARD (SAME STREET) at 18:00 (30m)
Shoot Day 6 | Sat 16 Jan 2027 | 1 | 08:00 | Scene | 13 | INT | Day | INT. FISHERIES SCHOOL - RADIO CLUB ROOM - DAY | Government Fisheries School Laboratory (Kalamassery) | Anjali examines the reel. Sticky-shed damage. It has to be baked before it can be played … | MEENU (Gauri Krishna), RAHUL (Aditya Nair), FATHIMA (Sabitha Rasheed), ANJALI (Nimisha Raghavan) | 1 4/8 | 2h 30m
Shoot Day 6 | Sat 16 Jan 2027 | 2 | 10:30 | Scene | 16 | INT | Night | INT. FISHERIES SCHOOL - RADIO CLUB ROOM - NIGHT | Government Fisheries School Laboratory (Kalamassery) | First playback. Static, a laugh, half a sentence in Mariamma's voice. Then the tape stops. | RAHUL (Aditya Nair), MARIAMMA (Divya Mathew), FATHIMA (Sabitha Rasheed), MEENU (Gauri Krishna), ANJALI (Nimisha Raghavan) | 1 5/8 | 3h 30m
Shoot Day 6 | Sat 16 Jan 2027 | 3 | 14:00 | Scene | 34 | INT | Night | INT. FISHERIES SCHOOL - RADIO CLUB ROOM - NIGHT | Government Fisheries School Laboratory (Kalamassery) | The second half of the reel plays. Mariamma relays positions. Varghese answers. | RAHUL (Aditya Nair), MARIAMMA (Divya Mathew), VARGHESE (Thampi Cherian), FATHIMA (Sabitha Rasheed), MEENU (Gauri Krishna), ANJALI (Nimisha Raghavan) | 1 7/8 | 3h
Shoot Day 6 | Sat 16 Jan 2027 | 4 | 13:00 | Lunch |  |  |  | LUNCH at 13:00 (1h)
Off Day | Sun 17 Jan 2027 | 0 |  | Off Day |  |  |  | Off day
Shoot Day 7 | Mon 18 Jan 2027 | 1 | 05:15 | Scene | 44 | EXT | Day | EXT. KADALKKARA HARBOUR - DAWN | Munambam Fishing Harbour | The boats go out. On the radio, Anjali reads the weather. | Old Fisherman, ANJALI (Nimisha Raghavan) | 6/8 | 2h 30m
Shoot Day 7 | Mon 18 Jan 2027 | 2 | 07:45 | Scene | 7 | EXT | Day | EXT. KADALKKARA HARBOUR - DAY | Munambam Fishing Harbour | Anjali walks the harbour. Fishermen remember her mother. Suresh runs a survey crew and do… | Old Fisherman, SURESH (Sajan Kuriakose), ANJALI (Nimisha Raghavan) | 1 5/8 | 4h
Shoot Day 7 | Mon 18 Jan 2027 | 3 | 11:45 | Scene | 21 | EXT | Day | EXT. KADALKKARA BEACH - DAY | Cherai Beach (north end) | The radio club flies an antenna kite. Anjali teaches them to call the harbour. | RAHUL (Aditya Nair), Harbour Clerk, MEENU (Gauri Krishna), FATHIMA (Sabitha Rasheed), ANJALI (Nimisha Raghavan) | 1 3/8 | 3h 30m
Shoot Day 7 | Mon 18 Jan 2027 | 4 | 07:30 | Breakfast |  |  |  | BREAKFAST at 07:30 (30m)
Shoot Day 7 | Mon 18 Jan 2027 | 5 | 12:30 | Lunch |  |  |  | LUNCH at 12:30 (45m)
Shoot Day 7 | Mon 18 Jan 2027 | 6 | 12:00 | Munambam harbour to Cherai beach |  |  |  | MUNAMBAM HARBOUR TO CHERAI BEACH at 12:00 (30m)
Shoot Day 8 | Tue 19 Jan 2027 | 1 | 17:00 | Scene | 23 | EXT | Night | EXT. KADALKKARA HARBOUR - NIGHT | Munambam Fishing Harbour | The village searches in the storm with torches. Suresh's crew brings the site floodlights. | RAHUL (Aditya Nair), FATHIMA (Sabitha Rasheed), SURESH (Sajan Kuriakose), ANJALI (Nimisha Raghavan) | 1 3/8 | 5h
Shoot Day 8 | Tue 19 Jan 2027 | 2 | 22:00 | Scene | 24 | EXT | Night | EXT. KADALKKARA JETTY - NIGHT | Munambam Fishing Harbour | Anjali at the jetty where her mother was last seen. | FATHIMA (Sabitha Rasheed) | 4/8 | 1h 15m
Shoot Day 8 | Tue 19 Jan 2027 | 3 | 23:15 | Scene | 25 | EXT | Night | EXT. HARBOUR BREAKWATER - NIGHT | Munambam Breakwater (stunt section) | Suresh finds Appachan at the end of the breakwater with Kannan, waving a torch at the sea… | SURESH (Sajan Kuriakose), APPACHAN (K. P. Gopinathan), ANJALI (Nimisha Raghavan) | 1 5/8 | 5h
Shoot Day 8 | Tue 19 Jan 2027 | 4 | 21:00 | Dinner |  |  |  | DINNER at 21:00 (45m)
Shoot Day 9 | Wed 20 Jan 2027 | 1 | 08:00 | Scene | 45 | EXT | Day | EXT. KADALKKARA BEACH - DAY | Cherai Beach (north end) | Low tide. Anjali and Appachan walk on the wet sand with Kannan. The end. | APPACHAN (K. P. Gopinathan), ANJALI (Nimisha Raghavan) | 4/8 | 2h
Shoot Day 9 | Wed 20 Jan 2027 | 2 | 10:00 | Scene | 38 | EXT | Night | EXT. KADALKKARA BEACH - DUSK | Cherai Beach (north end) | The village sets up for listening night: speakers, lanterns, a generator truck. | SURESH (Sajan Kuriakose), RAHUL (Aditya Nair), FATHIMA (Sabitha Rasheed), JOE (Lal Fernandez), MEENU (Gauri Krishna) | 1 | 3h
Shoot Day 9 | Wed 20 Jan 2027 | 3 | 13:00 | Scene | 40 | EXT | Night | EXT. KADALKKARA BEACH - NIGHT | Cherai Beach (north end) | Listening night. The reel plays over speakers. Suresh reads the fleet names. Joe stays. | MARIAMMA (Divya Mathew), VARGHESE (Thampi Cherian), SURESH (Sajan Kuriakose), LATHA (Reshmi Pillai), JOE (Lal Fernandez), APPACHAN (K. P. Gopinathan), FATHIMA (Sabitha Rasheed), RAHUL (Aditya Nair), MEENU (Gauri Krishna), ANJALI (Nimisha Raghavan) | 2 6/8 | 5h
Shoot Day 9 | Wed 20 Jan 2027 | 4 | 12:30 | Lunch |  |  |  | LUNCH at 12:30 (1h)
Shoot Day 9 | Wed 20 Jan 2027 | 5 | 18:30 | Dinner (extras fed first) |  |  |  | DINNER (EXTRAS FED FIRST) at 18:30 (45m)
Shoot Day 10 | Thu 21 Jan 2027 | 1 | 07:30 | Scene | 18 | EXT | Day | EXT. ST. ANTONY'S CHURCH - DAY | St. Antony's Church (Kadalkkara set dressing) | The memorial mass for the men lost in 1999. Suresh reads the names. Anjali stands at the … | SURESH (Sajan Kuriakose), FATHIMA (Sabitha Rasheed), ANJALI (Nimisha Raghavan) | 7/8 | 4h
Shoot Day 10 | Thu 21 Jan 2027 | 2 | 11:30 | Scene | 8 | INT | Day | INT. PORT TRUST OFFICE - DAY | Port Trust Office (heritage building, Willingdon Island) | Anjali asks for access to the station. The Port Officer refuses. Suresh watches. | PORT OFFICER (Ramesh Kaimal), SURESH (Sajan Kuriakose), ANJALI (Nimisha Raghavan) | 1 | 2h
Shoot Day 10 | Thu 21 Jan 2027 | 3 | 13:30 | Scene | 37 | INT | Day | INT. PORT TRUST OFFICE - DAY | Port Trust Office (heritage building, Willingdon Island) | Suresh asks Krishnadas to delay. Refused. He arranges power for one more night instead. | PORT OFFICER (Ramesh Kaimal), SURESH (Sajan Kuriakose) | 1 | 1h 30m
Shoot Day 10 | Thu 21 Jan 2027 | 4 | 11:00 | Church to Willingdon Island |  |  |  | CHURCH TO WILLINGDON ISLAND at 11:00 (45m)
Shoot Day 10 | Thu 21 Jan 2027 | 5 | 13:00 | Lunch |  |  |  | LUNCH at 13:00 (45m)
Shoot Day 10 | Thu 21 Jan 2027 | 6 | 16:00 | Willingdon Island to Vypin |  |  |  | WILLINGDON ISLAND TO VYPIN at 16:00 (40m)
Shoot Day 10 | Thu 21 Jan 2027 | 7 | 16:40 | Scene | 36 | INT | Day | INT. SURESH'S HOUSE - DAY | Suresh's House (Vypin) | Anjali brings Suresh the recording. He listens alone to his father's voice. | SURESH (Sajan Kuriakose), VARGHESE (Thampi Cherian), ANJALI (Nimisha Raghavan) | 1 2/8 | 2h
Shoot Day 11 | Fri 22 Jan 2027 | 1 | 10:00 | Scene | 19 | INT | Day | INT. POLICE OUTPOST - DAY | Police Outpost (set, Navodaya Studio Floor 2) | Latha warns Anjali about the trespass complaint, then quietly shows her the 1999 file. | LATHA (Reshmi Pillai), MARIAMMA (Divya Mathew), ANJALI (Nimisha Raghavan) | 1 2/8 | 2h
Shoot Day 11 | Fri 22 Jan 2027 | 2 | 12:00 | Scene | 32 | INT | Night | INT. POLICE OUTPOST - CELL - NIGHT | Police Outpost (set, Navodaya Studio Floor 2) | Joe confesses: the Port ordered the power cut. Mariamma kept going on a battery set. | LATHA (Reshmi Pillai), JOE (Lal Fernandez), ANJALI (Nimisha Raghavan) | 2 1/8 | 3h
Shoot Day 11 | Fri 22 Jan 2027 | 3 | 13:30 | Lunch (studio canteen) |  |  |  | LUNCH (STUDIO CANTEEN) at 13:30 (45m) · Canteen booked for 85.
Shoot Day 11 | Fri 22 Jan 2027 | 4 | 14:15 | Scene | 31 | EXT | Night | EXT. LIGHTHOUSE ROAD - NIGHT | Lighthouse Road (Puthuvype coast road) | Joe drives drunk. Latha's jeep pulls him over before the bend. | LATHA (Reshmi Pillai), JOE (Lal Fernandez) | 6/8 | 3h 30m
Shoot Day 11 | Fri 22 Jan 2027 | 5 | 16:30 | Studio to Njarakkal hospital |  |  |  | STUDIO TO NJARAKKAL HOSPITAL at 16:30 (50m)
Shoot Day 11 | Fri 22 Jan 2027 | 6 | 21:30 | Hospital to Lighthouse Road |  |  |  | HOSPITAL TO LIGHTHOUSE ROAD at 21:30 (20m)
Shoot Day 12 | Sat 23 Jan 2027 | 1 | 11:00 | Scene | 27 | INT | Day | INT. TALUK HOSPITAL - CORRIDOR - DAWN | Taluk Hospital Ward (closed wing, Njarakkal) | An uneasy truce. Suresh gives Anjali one day inside the station. | SURESH (Sajan Kuriakose), ANJALI (Nimisha Raghavan) | 7/8 | 1h 30m
Shoot Day 12 | Sat 23 Jan 2027 | 2 | 12:30 | Scene | 26 | INT | Night | INT. TALUK HOSPITAL - WARD - NIGHT | Taluk Hospital Ward (closed wing, Njarakkal) | Appachan on a drip. Suresh tells Anjali about his father and the Little Flower. | Nurse, SURESH (Sajan Kuriakose), APPACHAN (K. P. Gopinathan), ANJALI (Nimisha Raghavan) | 2 | 3h
Shoot Day 12 | Sat 23 Jan 2027 | 3 | 15:30 | Scene | 3 | INT | Day | INT. SOUNDWAVE STUDIO - BENGALURU - DAY | Soundwave Studio (Kochi stand-in for Bengaluru) | Present day. Anjali scrubs breaths out of a detergent ad. Fathima calls: Appachan is miss… | STUDIO PRODUCER (Karan Shetty), FATHIMA (Sabitha Rasheed), ANJALI (Nimisha Raghavan) | 1 6/8 | 2h 30m
Shoot Day 12 | Sat 23 Jan 2027 | 4 | 18:00 | Scene | 4 | INT | Night | INT. KSRTC BUS - MOVING - NIGHT | KSRTC Bus (process trailer, NH 66) | The overnight bus to Kochi. Anjali listens to an old cassette of her mother on air. | MARIAMMA (Divya Mathew), ANJALI (Nimisha Raghavan) | 5/8 | 2h
Shoot Day 12 | Sat 23 Jan 2027 | 5 | 14:00 | Lunch |  |  |  | LUNCH at 14:00 (45m)
Shoot Day 12 | Sat 23 Jan 2027 | 6 | 15:00 | Studio to Njarakkal hospital |  |  |  | STUDIO TO NJARAKKAL HOSPITAL at 15:00 (40m)
Shoot Day 12 | Sat 23 Jan 2027 | 7 | 21:00 | Hospital to Aroor lay-by |  |  |  | HOSPITAL TO AROOR LAY-BY at 21:00 (45m)
Off Day | Sun 24 Jan 2027 | 0 |  | Off Day |  |  |  | Off day
Shoot Day 13 | Mon 25 Jan 2027 | 1 | 16:30 | Scene | 1 | EXT | Night | EXT. OPEN SEA - NIGHT (1999) | Open Sea off Vypin (2 nautical miles out) | Prologue. A storm. Fishing boats in the swell and a woman's voice on the radio reading po… | MARIAMMA (Divya Mathew), VARGHESE (Thampi Cherian) | 1 1/8 | 5h
Shoot Day 13 | Mon 25 Jan 2027 | 2 | 21:30 | Scene | 35 | EXT | Night | EXT. OPEN SEA - LITTLE FLOWER - NIGHT (1999) | Open Sea off Vypin (2 nautical miles out) | Flashback. Varghese turns the fleet toward the river mouth, then goes back for the Seagul… | VARGHESE (Thampi Cherian), MARIAMMA (Divya Mathew) | 1 | 4h 30m
Shoot Day 13 | Mon 25 Jan 2027 | 3 | 15:30 (+1) | Boat transfer to the sea location |  |  |  | BOAT TRANSFER TO THE SEA LOCATION at 15:30 (50m)
Shoot Day 13 | Mon 25 Jan 2027 | 4 | 20:30 | Dinner on the support boat |  |  |  | DINNER ON THE SUPPORT BOAT at 20:30 (40m)
Shoot Day 14 | Tue 26 Jan 2027 | 1 | 07:00 | Scene | 42 | EXT | Day | EXT. COAST RADIO STATION - DAY | Coast Radio Station (Old Signal Station, Vypin) | Demolition. The excavator bites. The mast comes down. Appachan watches without fear. | APPACHAN (K. P. Gopinathan), SURESH (Sajan Kuriakose), FATHIMA (Sabitha Rasheed), LATHA (Reshmi Pillai), Old Fisherman, ANJALI (Nimisha Raghavan) | 1 2/8 | 5h
Shoot Day 14 | Tue 26 Jan 2027 | 2 | 12:00 | Scene | 43 | INT | Day | INT. FATHIMA'S TEA SHOP - DAY | Tea Shop and Toddy Shop Row (Mattancherry) | The radio club paints a sign: Low Tide Radio. Anjali calls Bengaluru and resigns. | STUDIO PRODUCER (Karan Shetty), FATHIMA (Sabitha Rasheed), RAHUL (Aditya Nair), MEENU (Gauri Krishna), ANJALI (Nimisha Raghavan) | 1 4/8 | 2h
Shoot Day 14 | Tue 26 Jan 2027 | 3 | 12:30 | Lunch |  |  |  | LUNCH at 12:30 (45m)
Shoot Day 14 | Tue 26 Jan 2027 | 4 | 13:15 | Vypin to Mattancherry |  |  |  | VYPIN TO MATTANCHERRY at 13:15 (45m)

## Days
Day | Date | Scenes | Pages | Estimated | Crew call | Shooting start | Target wrap | Estimated wrap | Locations | Cast | Call sheet | Day notes
Shoot Day 1 | Mon 11 Jan 2027 | 2 | 2 6/8 | 7h 30m | 07:00 | 08:00 | 18:00 | 14:00 | Coast Radio Station (Old Signal Station, Vypin) | SURESH, RAHUL, ANJALI, JOE | Final | Coast Radio Station interiors, day. Basement water pumped from 05:00.
Shoot Day 2 | Tue 12 Jan 2027 | 3 | 4 3/8 | 11h 45m | 14:00 | 15:00 | 01:00 (+1) | 20:15 | Coast Radio Station (Old Signal Station, Vypin) | MARIAMMA, YOUNG ANJALI, JOE, RAHUL, ANJALI | Final | 1999 operations room. Child performer works 15:00 to 19:30 only (scenes 2 and 32 first).
Shoot Day 3 | Wed 13 Jan 2027 | 3 | 3 7/8 | 10h 15m | 17:00 | 18:00 | 07:00 (+1) | 23:45 | Coast Radio Station (Old Signal Station, Vypin) | Guard, RAHUL, ANJALI, MARIAMMA, LATHA, APPACHAN | Final | Night at the station: scenes 12 and 40, then scene 5 at first light (06:10). Crew rest of 12 hours before day 4.
Shoot Day 4 | Thu 14 Jan 2027 | 5 | 6 | 11h 15m | 07:00 | 08:00 | 21:00 | 14:00 | Thomas House (private home, Chellanam) | FATHIMA, APPACHAN, ANJALI, MARIAMMA | Final | Thomas House all day. Blackout tents on the windows for the night scenes.
Shoot Day 5 | Fri 15 Jan 2027 | 4 | 5 6/8 | 12h 15m | 08:00 | 09:00 | 23:00 | 18:30 | Tea Shop and Toddy Shop Row (Mattancherry) | MEENU, RAHUL, FATHIMA, Nurse, ANJALI, JOE, SURESH | Final | Mattancherry street closure 10:00 to 23:00. Long day on one street; overtime agreed with the crew.
Shoot Day 6 | Sat 16 Jan 2027 | 3 | 5 | 10h | 07:00 | 08:00 | 20:00 | 14:00 | Government Fisheries School Laboratory (Kalamassery) | MEENU, RAHUL, FATHIMA, ANJALI, MARIAMMA, VARGHESE | Final | Fisheries school, Saturday. Reel playback cues from the sound department.
Off Day | Sun 17 Jan 2027 | 0 | 0/8 | [8 empty] | Rest day. Art department dresses the harbour; marine safety drill at 10:00.
Shoot Day 7 | Mon 18 Jan 2027 | 3 | 3 6/8 | 11h 45m | 04:00 | 05:00 | 18:30 | 12:30 | Munambam Fishing Harbour, Cherai Beach (north end) | Old Fisherman, ANJALI, SURESH, RAHUL, Harbour Clerk, MEENU, FATHIMA | Final | Harbour dawn for scene 43 before the auction, then scene 7; company move to Cherai for scene 21 (the antenna kite) in the afternoon wind.
Shoot Day 8 | Tue 19 Jan 2027 | 3 | 3 4/8 | 12h | 15:00 | 17:00 | 03:00 (+1) | 21:45 | Munambam Fishing Harbour, Munambam Breakwater (stunt section) | RAHUL, FATHIMA, SURESH, ANJALI, APPACHAN | Final | Storm night. Rain towers, wind machines, wave machine. Safety divers and ambulance on standby.
Shoot Day 9 | Wed 20 Jan 2027 | 3 | 4 2/8 | 11h 45m | 06:30 | 07:30 | 23:30 | 19:15 | Cherai Beach (north end) | APPACHAN, ANJALI, SURESH, RAHUL, FATHIMA, JOE, MEENU, MARIAMMA, VARGHESE, LATHA | Final | Cherai beach. Low tide 08:12 for scene 44. 300 extras from 16:00 for the listening night.
Shoot Day 10 | Thu 21 Jan 2027 | 4 | 4 1/8 | 11h 40m | 06:30 | 07:30 | 19:30 | 18:40 | St. Antony's Church (Kadalkkara set dressing), Port Trust Office (heritage building, Willingdon Island), Suresh's House (Vypin) | SURESH, FATHIMA, ANJALI, PORT OFFICER, VARGHESE | Final | Church at 07:30 (mass at 06:00 finishes first), then the Port Trust office and Suresh's house.
Shoot Day 11 | Fri 22 Jan 2027 | 3 | 4 1/8 | 10h 25m | 09:00 | 10:00 | 01:00 (+1) | 21:50 | Police Outpost (set, Navodaya Studio Floor 2), Lighthouse Road (Puthuvype coast road) | LATHA, MARIAMMA, ANJALI, JOE | Final | Studio outpost set, hospital wing, then the coast road at night. Sajan (SURESH) is unavailable today: scenes 25 and 26 moved to day 13.
Shoot Day 12 | Sat 23 Jan 2027 | 4 | 5 2/8 | 11h 10m | 10:00 | 11:00 | 01:00 (+1) | 21:45 | Taluk Hospital Ward (closed wing, Njarakkal), Soundwave Studio (Kochi stand-in for Bengaluru), KSRTC Bus (process trailer, NH 66) | SURESH, ANJALI, Nurse, APPACHAN, STUDIO PRODUCER, FATHIMA, MARIAMMA | Final | Soundwave Studio, the Njarakkal hospital (scenes 25 and 26 join from day 12), then the bus on the process trailer.
Off Day | Sun 24 Jan 2027 | 0 | 0/8 | [8 empty] | Rest day. Port Trust inspection of the station. Art department preps the demolition.
Shoot Day 13 | Mon 25 Jan 2027 | 2 | 2 1/8 | 11h | 13:00 | 16:30 | 02:00 (+1) | 21:10 | Open Sea off Vypin (2 nautical miles out) | MARIAMMA, VARGHESE | Final | Sea unit. Crew transfer by boat. Stop if swell is over 1.5 m.
Shoot Day 14 | Tue 26 Jan 2027 | 2 | 2 6/8 | 8h 30m | 06:00 | 07:00 | 18:00 | 14:00 | Coast Radio Station (Old Signal Station, Vypin), Tea Shop and Toddy Shop Row (Mattancherry) | APPACHAN, SURESH, FATHIMA, LATHA, Old Fisherman, ANJALI, STUDIO PRODUCER, RAHUL, MEENU | Final | Demolition: one take for the mast fall, three cameras. Then the tea shop for scene 42 (same story day).